## Summary
Field | Value
Application | 45Drives Storage Wizard
Platform Under Test | macOS
Edition | Standard
Tester
Date
Build / Version
OS Version
Server(s) Under Test
Network Environment
Total Tests | 106
Passed
Failed
Blocked / Skipped
Overall Result
Section | Test Count
1. Installation & First Launch | 3
2. Menu, Themes & Settings | 4
3. Set Up a Single Server - Simple Path | 9
4. Set Up a Single Server - Custom Path | 7
5. Set Up Multiple Servers (Bulk) | 4
6. Dashboard | 5
7. Manage Connections (Saved Logins) | 5
8. Server Management | 5
9. Back Up This Computer to the Server (Local Backups) | 12
10. Restore from a Local Backup | 3
11. Remote Backups - File Copy / Sync (Rsync) | 6
12. Remote Backups - ZFS Backup (Server-to-Server) | 3
13. Cloud Accounts & Server-to-Cloud Backup | 5
14. Off-Site Backups Over a WireShield Tunnel | 10
15. Restore from Remote & Cloud Backups | 6
16. Snapshots - Browse, Rollback & Delete | 4
17. Dashboard Insights & Log Viewer | 5
18. Automatic Updates | 3
19. Reliability & Edge Cases | 7

## Test Plan
Section | ID | Pass/Fail | Test Case | Steps | Expected Result | Actual Result | Notes / Failure Reason | Severity | Screenshot/Evidence
1. Installation & First Launch | 1.1 |  | Install the app on macOS | 1. Open the downloaded .dmg. 2. Drag 45Drives Storage Wizard into the Applications folder. 3. Launch the app from Applications. 4. If macOS asks to confirm opening the app, allow it. | The app installs and launches to the Dashboard with no 'damaged app' or unidentified-developer block. The window title reads '45Drives Storage Wizard v<version>'.
1. Installation & First Launch | 1.2 |  | First launch shows a usable empty state | 1. Launch the app on a computer that has never run it before. 2. Look at the Dashboard and the Quick Actions panel on the right. | The Dashboard loads with no saved servers. Quick Actions lists Setup Single Server, Setup Multiple Servers, Manage Backups, Logs and Settings, and a Getting Started card gives you a clear next step. Nothing is blank, broken, or stuck loading.
1. Installation & First Launch | 1.3 |  | Server discovery works with macOS local network permission | 1. Power on an unconfigured 45Drives server on the same network. 2. Launch the app and click Setup Single Server in Quick Actions. 3. When macOS asks for permission to find devices on the local network, allow it. 4. Step through to 'Select a 45Drives Server to Setup'. | The server appears in the 'Select a server' dropdown as 'ServerName (IP)' within about a minute. If permission is denied, the app gives a clear message instead of an empty list.
2. Menu, Themes & Settings | 2.1 |  | Menu navigation opens the right screens | 1. Click the hamburger button (the three-line icon) in the top-right corner. 2. Under Navigation, click each item in turn - Dashboard, Setup Wizard, Backup Manager, View Logs, Settings - returning to the Dashboard between each. | The menu panel slides out showing the Navigation and Appearance sections. Each item opens its intended screen with no dead buttons and no error screens.
2. Menu, Themes & Settings | 2.2 |  | Theme swatches and the Light / Dark toggle apply and persist | 1. Open the menu and, under Appearance, click each of the four swatches in turn - 45Drives, 45Homelab, 45Pro, 45Studio. 2. Switch the Light / Dark toggle beside them. 3. Visit the Dashboard and the Backup Manager. 4. Quit and relaunch the app. | The whole app recolours to match the selected swatch and the light/dark choice, text stays readable everywhere, and the choice is still in effect after restart.
2. Menu, Themes & Settings | 2.3 |  | A settings change is saved and persists | 1. Open Settings from the menu. 2. Under Client > Display, change Server display format and turn Show notification toasts off. 3. Under Network > Connection, turn Fallback network scan on and change SSH Connection timeout. 4. Confirm 'Unsaved changes' appears in the footer and that Save is only enabled once you edit something, then click Save. 5. Quit, relaunch, and reopen Settings. | The footer shows 'Unsaved changes' as soon as you alter anything, Cancel closes without applying, and every saved value is still set after restart.
2. Menu, Themes & Settings | 2.4 |  | Reset All Settings returns everything to default | 1. With two or three settings changed, open Settings > System > Advanced. 2. Click Reset All Settings at the bottom of that panel and confirm. | Every preference returns to its default value, the note 'This resets all preferences to their defaults. Saved servers are not affected.' holds true, and the app keeps working normally.
3. Set Up a Single Server - Simple Path | 3.1 |  | Walk the Setup Wizard to the discovery step | 1. Click Setup Single Server in Quick Actions. 2. Step forward through Welcome, Unboxing, Plug-In Power, Plug-In Ethernet and Power On using Next, and use Back once to confirm it works. 3. Hover a '?' icon on any step. 4. Stop on the 'Select a 45Drives Server to Setup' step. | Every step advances cleanly with working Back and Next, the '?' icon shows Houston Commander's extra guidance, and the discovery step lists your unconfigured server in the 'Select a server' dropdown as 'ServerName (IP)'.
3. Set Up a Single Server - Simple Path | 3.2 |  | Connect to the discovered server | 1. Choose your server in 'Select a server'. If it is not listed, click Rescan Servers; if it still does not appear, type its address into 'Connect manually via IP'. 2. Enter the Username (defaults to root) and Password, using the eye icon to check what you typed. 3. Enter a deliberately wrong password and click Next. 4. Correct the password and click Next again. | The wrong password is rejected with a clear message and a 'Troubleshooting steps' section, with no crash. With the correct password the button reads 'Installing...' and status messages appear, then the Super Simple Setup 'Set Up Your Server' screen opens inside the app window.
3. Set Up a Single Server - Simple Path | 3.3 |  | Choose SIMPLE and check Storage Server Set Up validation | 1. On 'Set Up Your Server', click the SIMPLE card (badged Recommended). 2. On the Storage Server Set Up step try each of these in turn: a Server Name containing a space, a User Name of 'root', a Password of 'password', a Confirm Password that does not match, and a Network Folder Name containing a space. | Each invalid entry is blocked with a clear, plain-English message, and Next stays disabled until the entry is fixed.
3. Set Up a Single Server - Simple Path | 3.4 |  | Complete the Storage Server Set Up step | 1. Enter a valid Server Name, User Name, Password and Confirm Password, and a Network Folder Name. 2. Leave 'Use the same password for root account?' ticked, then untick it and confirm the Root Password and Confirm Root Password fields appear. Re-tick it. 3. Check the Folder Preview line. 4. Click Next and read the save-your-credentials dialog. 5. Click OK, Proceed. | Folder Preview shows exactly how the share will appear in a file browser, for example \\myserver.local\data. The dialog warns you to record your username, password and especially the root password, and OK, Proceed moves to the Storage Drive Summary step.
3. Set Up a Single Server - Simple Path | 3.5 |  | Storage Drive Summary shows the real hardware | 1. On the Storage Drive Summary step, review the drive view on the left and the Drive Properties and Issues panels on the right. 2. Click an individual drive. 3. Physically remove a drive, wait a few seconds for the view to refresh, then reseat it. | The drive count matches the physical server. Clicking a drive fills Drive Properties with its model, serial, capacity, type, health, rotation rate and firmware. Issues reads 'No issues found.' in green when healthy; removing a drive raises an issue naming the slot and blocks Next, and reseating it clears the issue.
3. Set Up a Single Server - Simple Path | 3.6 |  | Wipe all drives | 1. Using a server whose drives contain previous partitions, confirm the 'Wipe all drives' checkbox appears with a summary of the method and the slot count. 2. Click Change method and read the Full erase and Quick wipe descriptions. 3. Choose Quick wipe and continue with the setup. | The Wipe Method modal describes both options clearly, Quick wipe is applied, and an 'Erasing Selected Drives' step is inserted into the setup checklist and completes without failing.
3. Set Up a Single Server - Simple Path | 3.7 |  | Active Backup - Split Pools | 1. On a server with 6 or more drives, tick Split Pools in the Active Backup section. 2. Read the snapshot retention text and review the capacity table below it. 3. If a server with fewer than 6 drives is available, confirm the checkbox is disabled there. | With 6 or more drives the checkbox enables, the text explains hourly (kept 1 day), daily (kept 1 week) and weekly (kept 1 month) snapshots, and the capacity table lists a Storage row and a Backup row with failure tolerance and usable space. With fewer than 6 drives the checkbox is disabled and explains why.
3. Set Up a Single Server - Simple Path | 3.8 |  | Review the Summary and apply the configuration | 1. Check the Summary step - System Summary, Samba Summary, Storage ZFS and Backup ZFS - against what you entered. 2. Reveal the hidden password with the eye icon. 3. Read the orange data-loss warning, then click Complete Setup. 4. Watch the 'Setting Up Server' checklist through to the end. | The summary matches your input. Every checklist row turns green, with no failures. If you changed the Server Name the server reboots afterwards and the app explains that this is expected.
3. Set Up a Single Server - Simple Path | 3.9 |  | Verify the finished server | 1. On the completion screen confirm both buttons are present - Configure Backups and Setup More Storage Servers - then click Configure Backups. 2. Return to the Dashboard. 3. From this computer's file browser, open the network folder using the path shown in Folder Preview and the User Name and Password you created. 4. Copy a test file into it. | Configure Backups opens the Backup Manager. The server is listed in Saved Servers with a green online dot. The share opens with your credentials and accepts the test file.
4. Set Up a Single Server - Custom Path | 4.1 |  | Custom Step 1: Server Info | 1. On a second fresh unconfigured server, click the CUSTOM card (badged Advanced) on 'Set Up Your Server'. 2. Fill in Server Name, Admin Username, Admin Password and Confirm Password. 3. Set a Timezone and leave Disable Root SSH and Sync Time via NTP ticked. 4. Try an Admin Username that is reserved or already in use. | Fields validate the same way as the Simple path, the reserved or duplicate username is rejected with a clear message, and Next advances to ZFS Configuration.
4. Set Up a Single Server - Custom Path | 4.2 |  | Custom Step 2: ZFS Configuration | 1. Choose a RAID Level (for example raidz2). 2. Select fewer drives than the minimum, then enough drives, watching the 'Select Drives (N selected, minimum M)' heading. 3. Under Storage Pool, change Pool Name and set Compression. 4. Under Dataset, set Name. | The heading tracks selected drives against the minimum for the chosen RAID Level. Next is blocked below the minimum and enabled once satisfied. Pool Name, Compression and the dataset Name all accept the changes.
4. Set Up a Single Server - Custom Path | 4.3 |  | Enable Backup Pool and assign drives | 1. On a server with 6 or more drives, tick Enable Backup Pool. 2. Use the Pool column in the drive table to assign drives to Storage and to Backup. 3. Configure the Backup pool's own Pool Name, Compression and dataset options. | The Pool column appears, each drive can be assigned to Storage or Backup, and a matching Backup pool configuration section appears, described as the active backup where the main storage pool is replicated.
4. Set Up a Single Server - Custom Path | 4.4 |  | Custom Step 3: Users & Groups | 1. Click + Add Group and enter a group name. 2. Click + Add User, give the user a Username and Password, and tick the new group under Groups. 3. Click + Add User again and enter a username that already exists or is reserved. | The admin user from Step 1 is listed automatically with an Admin badge. The new group and user are accepted. The duplicate or reserved username is rejected with a clear message.
4. Set Up a Single Server - Custom Path | 4.5 |  | Custom Step 4: Samba Shares | 1. Confirm the share badged Primary has a locked Share Name that cannot be edited. 2. Click + Add Share and give the new share a Share Name, Path and Description. 3. Under Access, untick All users and tick only the extra user you created in the previous step. | The Primary share name cannot be renamed. The second share is added and its access is limited to the chosen user.
4. Set Up a Single Server - Custom Path | 4.6 |  | Custom Step 5: Summary and apply | 1. Review the Custom Summary, expanding the Drives, Pool Options and Dataset panels. 2. Read the orange data-loss warning, then click Complete Setup. 3. Watch the 'Setting Up Server' checklist finish. | The summary matches everything you configured and every checklist row completes green.
4. Set Up a Single Server - Custom Path | 4.7 |  | Verify the custom result on the server | 1. Open the finished server's Server Management page. 2. Check the Storage tab for the pool name and RAID level, the Users & Groups tab for your users and groups, and the Samba tab for both shares. 3. From this computer, open the second share with the extra user's credentials, then try it with a user that should not have access. | Everything on the server matches the custom configuration. The permitted user can open the second share; the non-permitted user is refused.
5. Set Up Multiple Servers (Bulk) | 5.1 |  | Fill in Global Defaults and apply them | 1. Click Setup Multiple Servers in Quick Actions. 2. Click + Add Server twice, once for each unconfigured server. 3. In Global Defaults, fill in SSH Username, SSH Password, SMB Username and SMB Password. 4. Click 'Apply to all servers missing values'. 5. Change one value on a single server card. | The page is titled 'Bulk Server Setup'. Both cards are added, Global Defaults populate every blank field on both cards, and the per-server edit is preserved rather than being overwritten.
5. Set Up Multiple Servers (Bulk) | 5.2 |  | Export and import a bulk template | 1. Click Export Template and save the JSON file. 2. Leave the Bulk Server Setup page and come back, or clear the cards. 3. Click Import Template and load the saved file. | The exported file is created and importing it restores the same server cards and values.
5. Set Up Multiple Servers (Bulk) | 5.3 |  | Run the bulk deployment | 1. Start the deployment from the sticky action bar at the bottom of the page. 2. Watch the total, done and failed counters and the name of the server currently running. 3. Wait for it to finish. | The action bar names the server currently running and the done count increases. Both servers finish successfully and appear in Saved Servers on the Dashboard.
5. Set Up Multiple Servers (Bulk) | 5.4 |  | One server failing does not stop the others | 1. Set up two server cards, giving one card a deliberately wrong SSH Password. 2. Run the deployment. | The bad card is counted as failed with a clear reason. The other server still completes successfully.
6. Dashboard | 6.1 |  | Saved Servers shows correct live status | 1. On the Dashboard, look at the Saved Servers card with a configured server powered on. Check the row shows a status dot, the server name, a favourite star, and username@host with the share name and when it was last used. 2. Power the server off (or unplug its network cable) and wait for the card to refresh. 3. Power it back on. | The dot is green while the server is reachable, grey when it is not, and returns to green once it is back.
6. Dashboard | 6.2 |  | Selecting a server fills the Storage and System Health cards | 1. Single-click a row in Saved Servers. 2. Look at the Storage and System Health cards below Saved Servers. | The row is marked Viewing, the status strip's 'Viewing: <server name>' line names it, and the Storage and System Health cards show capacity usage and health that match the server you configured.
6. Dashboard | 6.3 |  | Quick Actions open the right destinations | 1. Click each Quick Action in turn - Setup Single Server, Setup Multiple Servers, Manage Backups, Logs and Settings - returning to the Dashboard between each. | Each button opens its intended destination: the Setup Wizard, Bulk Server Setup, the Backup Manager, the Log Viewer and the Settings modal. No dead buttons and no error screens.
6. Dashboard | 6.4 |  | Add a server manually with + Add | 1. In the Saved Servers card header, click + Add. 2. Enter the IP address of a server that is already configured and save. | The server is added to Saved Servers and shows a reachability dot like any other row.
6. Dashboard | 6.5 |  | Saved servers and settings survive a restart | 1. With at least one saved server on the Dashboard, give it a display name and mark it as a favourite in Settings > Servers > Saved. 2. Quit the app completely. 3. Launch it again. | The saved server, its display name, its favourite star and all your settings are still there.
7. Manage Connections (Saved Logins) | 7.1 |  | Saved logins are listed with accurate counters | 1. Click Manage Connections in the Saved Servers card header. 2. Read the four counters - Total Saved Logins, Unique Hosts, Active (<30d) and Stale (30+d). 3. Expand a host group. | The page reads 'Manage saved server logins. Stored securely on this device.' Credentials are grouped by host with a reachability indicator, each row shows the saved username, no password is shown in readable form, and the counters match the rows listed.
7. Manage Connections (Saved Logins) | 7.2 |  | Credentials are remembered after a restart (macOS) | 1. Connect to a server and let the app save the credentials. 2. Quit and relaunch the app. 3. Connect to the same server again. If macOS asks for Keychain access, allow it. | The app connects without asking you to re-enter the password. If macOS asks for Keychain access, allow it.
7. Manage Connections (Saved Logins) | 7.3 |  | Search and the All / Active / Stale / Orphaned filters work | 1. Type a host, username or label into the search box. 2. Click each filter in turn - All, Active, Stale, Orphaned. | Search narrows the list to matching entries, and each filter shows only the credentials in that state.
7. Manage Connections (Saved Logins) | 7.4 |  | Forget a saved login | 1. Open the '...' menu on a credential row and remove that login. 2. Connect to that server again. | The entry disappears from the list and the app asks for the password again on the next connection.
7. Manage Connections (Saved Logins) | 7.5 |  | 30-day staleness and Clean Stale - NOT TESTED | A saved login only becomes stale after 30 days without use, which cannot be reached inside a normal test window. This covers the Stale (30+d) counter, the amber stale banner on the Dashboard's Saved Servers card, and the 'Clean N Stale' button. Mark this row SKIPPED and take no action. | N/A - deliberately out of scope for this test pass.
8. Server Management | 8.1 |  | Open the management page and read its status | 1. On the Dashboard, hover a row in Saved Servers and click the gear icon. 2. Go back and double-click the same row. 3. Read the page header. | The Server Management page opens both ways. It shows 'Probing server...' briefly, then the server name, the 'username@host - ip' subtitle, a green status dot while online, and the Edit and Refresh buttons.
8. Server Management | 8.2 |  | All six tabs load real data | 1. Visit each tab in turn: Connection, Network, Storage, Users & Groups, Samba, System. | Every tab loads without an error or an endless spinner. Connection shows Nickname, Host, Hostname, IP Address, the Admin Login and the Samba Share details; Network shows interfaces, DNS servers and VPN Tunnels (WireGuard); Storage shows the pool and dataset with capacity; Users & Groups, Samba and System all match the server you configured.
8. Server Management | 8.3 |  | Staged Changes are held until you save them | 1. Click Edit, then change a field - for example the Nickname on Connection, or add a user on Users & Groups. 2. Confirm the Staged Changes panel slides in from the right listing the old and new value with a 'local' or 'server' tag. 3. Click Save N Changes. 4. Click Refresh. | The change is held as pending rather than applied immediately, any password is masked in the panel, saving succeeds, and after refreshing the change is present on the server.
8. Server Management | 8.4 |  | Discard All abandons staged changes | 1. Stage two changes. 2. Click the X on one entry to drop just that change. 3. Click Discard All. 4. Click Refresh. | The X removes only that one entry, Discard All drops the rest, and after refreshing the server and the app are unchanged.
8. Server Management | 8.5 |  | Offline server is handled gracefully | 1. Open a saved server's Server Management page while that server is powered off. | The probe fails with a clear, plain-English reason and a Retry button. The app does not hang, crash, or show a raw technical error.
9. Back Up This Computer to the Server (Local Backups) | 9.1 |  | Create Backup Task step | 1. Open the Backup Manager, stay on the Local Backups tab, and click New Backup. 2. In Back Up Location choose your server's share, shown as \\ServerName\ShareName. Use the refresh icon if it is not listed yet. 3. Leave Schedule Type on Simple and set Backup Interval to Hourly. 4. Under Folder Selection click the + button and add two folders containing test files. 5. Type a friendly backup name for each folder. | The share is listed and selectable. Both folders appear in the list with their source path, a name input, a calendar button and a remove button. Next is only enabled once at least one folder is selected.
9. Back Up This Computer to the Server (Local Backups) | 9.2 |  | Overlapping folder selections are blocked | 1. Click + and add a folder that is already in the list. 2. Click + and add a subfolder of one already in the list. 3. Click + and add a parent of one already in the list. | Each attempt is refused with a plain message: 'This path is already added.', 'A subfolder of this folder is already added. Please remove it first.' and 'A parent folder is already added. You cannot add a subfolder.'
9. Back Up This Computer to the Server (Local Backups) | 9.3 |  | Samba Login step | 1. On the Samba Login step, check the Destination line reads \\ServerName\Share. 2. Enter a deliberately wrong Password and continue. 3. Enter the User Name and Password you created during Super Simple Setup. | The wrong credentials are refused with 'Invalid credentials. Please check your username and password.' The correct credentials are accepted and the wizard moves to Summary.
9. Back Up This Computer to the Server (Local Backups) | 9.4 |  | Summary warns about Full Disk Access (macOS) | 1. Read the warning banner on the Summary step. 2. Finish the wizard. 3. Follow the instruction to grant scheduled backups (cron) Full Disk Access in System Settings > Privacy & Security > Full Disk Access. | The Summary clearly explains the Full Disk Access requirement in plain language and the task is created.
9. Back Up This Computer to the Server (Local Backups) | 9.5 |  | Summary, then Complete | 1. On Summary, check the Backup Location line and each task card's Source, Frequency and Starts values. 2. Finish the wizard. 3. On the final step, click Go To Backup Manager. | The Summary matches what you entered, the final step reads 'Complete! Your Backup Plan is Now Active.' with Go to Dashboard and Go To Backup Manager buttons, and the new tasks are listed in the Local Backups table with the correct Name, User, Source, Destination, Freq, Status, Last Run and Next Run.
9. Back Up This Computer to the Server (Local Backups) | 9.6 |  | Run a backup immediately with Run Now | 1. Select the task and click Run Now. 2. Watch the 'N backups in progress' panel at the bottom. 3. When it finishes, open the network folder on the server from this computer's file browser. | A progress bar and percentage are shown while it runs, the task reports success, and every file from the source folders is on the server with matching contents.
9. Back Up This Computer to the Server (Local Backups) | 9.7 |  | A scheduled backup runs on its own | 1. Leave the hourly task in place and add a new file to one of the source folders. 2. Wait for the scheduled time to pass without touching the app. 3. Check the task's Last Run column and the folder on the server. | The backup runs automatically at the scheduled time and the new file appears on the server.
9. Back Up This Computer to the Server (Local Backups) | 9.8 |  | Scheduled backup still runs with the app closed | 1. With a scheduled task in place, quit the app completely. 2. Wait for the next scheduled run to pass. 3. Relaunch the app, check the task's Last Run, then check the folder on the server. | The backup ran while the app was closed and the files reached the server.
9. Back Up This Computer to the Server (Local Backups) | 9.9 |  | Edit, Enabled toggle, and Delete | 1. Select exactly one task and click Edit; change its name and schedule, then save. 2. Turn the Enabled toggle off and wait past the next scheduled time. 3. Turn it back on, then select the task and click the trash icon to delete it. | The edits are saved and shown in the table. Edit is only enabled when exactly one task is selected. While disabled the task does not run. Deleting removes it from the table and it does not run again.
9. Back Up This Computer to the Server (Local Backups) | 9.10 |  | Task logs are readable | 1. Select a task that has run and click Logs. | The run history is shown with timestamps and a clear success or failure result for each run.
9. Back Up This Computer to the Server (Local Backups) | 9.11 |  | Backup handles awkward files | 1. Add files to a source folder with: a very long name, accented and non-English characters, spaces, and a file over 1 GB. 2. Run the backup. | All files are copied with their names intact and the large file transfers completely without corrupting the run.
9. Back Up This Computer to the Server (Local Backups) | 9.12 |  | Backup fails clearly when the server is unreachable | 1. Power off the server, or disconnect it from the network. 2. Run the backup task. 3. Bring the server back and run it again. | The task reports a clear failure explaining that the server could not be reached, the app stays usable, and the next run succeeds once the server is back.
10. Restore from a Local Backup | 10.1 |  | Browse a local backup with View/Restore | 1. On the Local Backups tab select a completed task and click View/Restore. 2. Navigate into subfolders and back out again using the breadcrumb path. | The backed-up folder structure is shown and navigation works in both directions.
10. Restore from a Local Backup | 10.2 |  | Restore a single file to this computer | 1. Delete or rename a file in the original source folder. 2. In the backup browser, select that file and restore it. 3. Open the restored file. | The file is restored to this computer and its contents are identical to the original.
10. Restore from a Local Backup | 10.3 |  | Restore a whole folder to this computer | 1. Select an entire backed-up folder and restore it. | Every file and subfolder is restored with the correct structure and contents.
11. Remote Backups - File Copy / Sync (Rsync) | 11.1 |  | Connect to a server | 1. Switch to the Remote Backups tab and note the message 'Select a server above to view remote backups.' 2. Pick your server from the 'Select Server...' dropdown; favourites appear in their own group. 3. Click Connect and enter a deliberately wrong Password. 4. Enter the correct Username and Password. | The wrong password is refused with a clear message. The correct password connects and the server's backup task list loads, with a footer summary such as '6 tasks - 1 running - 2 disabled'.
11. Remote Backups - File Copy / Sync (Rsync) | 11.2 |  | Connect using an SSH private key | 1. Click Disconnect, then Connect again. 2. In the login dialog tick 'Authenticate with SSH private key', browse to a valid key, and supply the Key Passphrase if the key has one. | The app connects successfully using the key.
11. Remote Backups - File Copy / Sync (Rsync) | 11.3 |  | The two toolbars and their two gear icons are distinguishable | 1. With a server connected, identify the top toolbar (Dashboard, the Local Backups / Remote Backups tabs, the server dropdown, Connect, Disconnect, Forget, Restore, Snapshots and a gear) and the Task Scheduler toolbar below it (New Backup, Delete Tasks, refresh, a gear and the notification bell). 2. Click the gear at the far right of the top toolbar, then close it. 3. Click the gear beside the refresh icon in the lower toolbar. | The top gear opens the desktop app's Settings (saved servers, display, connection, log retention). The lower gear opens the remote backup Settings with Retry on Failure - Wait before retrying, Total attempts and Apply to Existing Backups - and Status Refresh with Fast / Normal / Slow.
11. Remote Backups - File Copy / Sync (Rsync) | 11.4 |  | Create a File Copy / Sync (Rsync) task | 1. Click New Backup and enter a Task Name. 2. Set Task Template to 'File Copy / Sync (Rsync)'. 3. Under 'What do you want to copy?', pick a folder from the From (Source) dropdown and check the Scope, Full Path and User line beneath it. 4. Enter a path in To (Target). 5. Under 'Copy to another server (optional)', enter the second server's Server address, User and Password, then click Test Connection (SSH). 6. Set the schedule in the Schedule Task panel and click Create Task. | The From (Source) dropdown lists folders already backed up to this server from the desktop app. Test Connection (SSH) reads 'Testing...' and then reports success. The Schedule Task panel shows a plain-English preview and highlights the matching days on its calendar. The task is created and appears in the list with Type 'Server-to-Server'.
11. Remote Backups - File Copy / Sync (Rsync) | 11.5 |  | Run the Rsync task and verify the data | 1. Select the task and click Run Now, confirming 'Do you wish to run this task now?'. 2. Watch the Status dot, the Last Run column and the 'N backups in progress' strip. 3. When it completes, check the To (Target) path on the destination server. | Status turns blue while running with Last Run showing 'Running now...', then a 'Task Successful' notification appears. All files are present on the destination server with matching contents.
11. Remote Backups - File Copy / Sync (Rsync) | 11.6 |  | Disconnect and Forget a remote server | 1. Click Disconnect. 2. Click Forget for that server, then Connect to it again. | Disconnect returns to the not-connected state. After Forget, the login dialog asks for credentials again on the next connection.
12. Remote Backups - ZFS Backup (Server-to-Server) | 12.1 |  | Create a ZFS Backup (Server-to-Server) task | 1. Click New Backup, enter a Task Name, and set Task Template to 'ZFS Backup (Server-to-Server)'. 2. Read the ZFS Backup information panel that appears. 3. Under 'Which folder do you want to back up?', choose a Pool and a Dataset (Folder). 4. Under 'Where should the backup go?', enter the Server address, User and Port, then choose the Destination Dataset. 5. Click Test Connection (SSH), set the schedule, and click Create Task. | The Pool, Dataset (Folder) and Destination Dataset dropdowns populate from the real servers, Test Connection (SSH) succeeds, and the task is created with Type 'ZFS to ZFS Backup'.
12. Remote Backups - ZFS Backup (Server-to-Server) | 12.2 |  | Run the replication and verify it | 1. Select the task and click Run Now. 2. When it finishes, check the destination server's dataset. | The task succeeds and the destination dataset contains the replicated data and a matching snapshot.
12. Remote Backups - ZFS Backup (Server-to-Server) | 12.3 |  | The second run sends only the changes | 1. Add a file to the source dataset. 2. Run the task again. 3. Compare how long it takes against the first run and check the destination. | The second run is noticeably faster than the first, completes successfully, and the new file appears on the destination.
13. Cloud Accounts & Server-to-Cloud Backup | 13.1 |  | Add a cloud account with sign-in (OAuth) | 1. Click New Backup, set Task Template to 'Cloud Backup', and in 'Choose your cloud account' click Add/Manage Cloud Accounts. 2. Click Add and, under 'Choose a provider', pick Dropbox, Google Drive or Google Cloud Storage. 3. Under 'Name your account', type a name you will recognise. 4. Click 'Authenticate with <Provider>' and complete the sign-in in the browser window that opens. 5. Click Save Account. | The sign-in completes, the button changes to Reset OAuth, and the account is listed under 'Your accounts' with the correct provider logo and name.
13. Cloud Accounts & Server-to-Cloud Backup | 13.2 |  | Add a cloud account using keys | 1. Click Add and expand 'Advanced: more providers'. 2. Pick Amazon S3, Wasabi or Backblaze B2 and name the account. 3. Expand Advanced and enter the Access Key ID, Secret Access Key and any required region, endpoint or provider flavour. 4. Click Save Account. 5. Repeat with a deliberately wrong key, and use Clear to reset the form. | The account is saved and listed. Wrong keys are reported clearly rather than being saved as a broken account. Clear empties the form.
13. Cloud Accounts & Server-to-Cloud Backup | 13.3 |  | Edit and delete a cloud account | 1. Select an account on the left, click Edit, rename it and click Save Changes. 2. Expand 'Show parameters' to inspect the raw provider settings. 3. Select an account you no longer need and click Delete. | The rename is reflected everywhere the account is offered, the parameters are visible, and Delete removes it so it is no longer selectable in a backup task.
13. Cloud Accounts & Server-to-Cloud Backup | 13.4 |  | Create a Cloud Backup task | 1. Click New Backup, enter a Task Name, and set Task Template to 'Cloud Backup'. 2. Under 'What do you want to copy?' pick a Local folder on the server. 3. Under 'Choose your cloud account' pick a saved Cloud account and confirm its provider logo appears. 4. Under 'How should we transfer?' choose Copy. 5. Under 'Where do you want to copy it to?' enter a Cloud folder path such as my-bucket/backups/. 6. Set the schedule and click Create Task. | The task is created and appears in the list with Type 'Cloud Backup' and the correct Source and Dest in the Details column.
13. Cloud Accounts & Server-to-Cloud Backup | 13.5 |  | Run the cloud backup and verify it | 1. Select the task and click Run Now. 2. When it finishes, sign in to the cloud provider directly and look in the Cloud folder. | The task succeeds and all files are present in the cloud folder with matching contents.
14. Off-Site Backups Over a WireShield Tunnel | 14.1 |  | Open WireShield from a backup task | 1. Click New Backup and set Task Template to 'File Copy / Sync (Rsync)'. 2. Enter a Task Name and pick a From (Source) folder. 3. In the header of the 'Copy to another server (optional)' card, click Connect Off-Site Server. | WireShield opens inside the app on the Off-Site Connections page, with the banner 'Pick the off-site server you want to back up to, and we'll fill it in for you.' and a Back to Task Scheduler button, so it is clear you are choosing a destination for the task in progress.
14. Off-Site Backups Over a WireShield Tunnel | 14.2 |  | Check This Server pre-flight | 1. Expand 'Connect to an Off-Site Server'. 2. Click Check This Server and wait for it to finish. | The button reads 'Checking...' and then shows Ready (green) or Needs Attention (amber), with a detail box explaining the result in plain English. If the port could not be opened automatically, an amber notice names the exact UDP port to forward.
14. Off-Site Backups Over a WireShield Tunnel | 14.3 |  | Create a pairing code on the first server | 1. In 'Name this connection', type a name such as offsite-backup. 2. Set 'Code expires after'. 3. Click 'Start Here - Create a Code'. 4. Click Copy Code. | The button reads 'Creating Code...', then the 'Your Connection Code' screen shows a 6-character code. Copy Code changes to Copied, and a countdown reads 'Waiting for the other server to connect - code expires in M:SS'.
14. Off-Site Backups Over a WireShield Tunnel | 14.4 |  | Join from the second server | 1. On the second server, open WireShield, expand 'Connect to an Off-Site Server' and click 'I Already Have a Code'. 2. Type the 6-character code and click Connect. 3. Watch both servers. | The input converts to uppercase and the connection is named automatically to match the first server. Both ends show 'Setting up the secure connection...' and then a green Connected result. The connection is listed under Off-Site Connections with a green dot, the label Connected, and a count of servers on the other end.
14. Off-Site Backups Over a WireShield Tunnel | 14.5 |  | Use This Connection hands the tunnel IP back to the task | 1. With the 'Pick the off-site server you want to back up to' banner showing, click Use This Connection on the paired connection row. | You are returned to the Backup Manager, your in-progress task is restored exactly as you left it, and Server address is filled in with the tunnel IP automatically.
14. Off-Site Backups Over a WireShield Tunnel | 14.6 |  | Hand back by picking a specific peer | 1. Repeat the previous test, but first click the connection row to expand it. 2. Click the peer server row, which shows a 'Use ->' hint. | The same handoff happens, and the Server address filled into the task matches the tunnel IP of the peer you chose - for example 10.45.0.2.
14. Off-Site Backups Over a WireShield Tunnel | 14.7 |  | Leaving WireShield without choosing does not lose the task | 1. Open WireShield from a part-filled task again. 2. Click Back to Task Scheduler without selecting a connection. | You are returned to the task with everything you had already entered still intact and Server address unchanged.
14. Off-Site Backups Over a WireShield Tunnel | 14.8 |  | First-time SSH setup over the tunnel | 1. With the tunnel IP in Server address, enter the destination server's User. 2. When the 'First-time setup' panel asks for that account's password, supply it. 3. Click Test Connection (SSH). | The one-time key exchange completes, the footer warning 'SSH login must be configured before remote copies can work.' clears, and Test Connection (SSH) reports success.
14. Off-Site Backups Over a WireShield Tunnel | 14.9 |  | Run an Rsync task over the tunnel | 1. Finish and save the Rsync task that uses the tunnel IP. 2. In WireShield, expand the connection and note the peer's 'Received ... - Sent ...' counters. 3. Run the task and wait for it to finish. 4. Check the counters again and check the To (Target) path on the destination server. | The task succeeds, the files arrive on the destination server, and the Received / Sent counters increase, showing the transfer really went through the tunnel.
14. Off-Site Backups Over a WireShield Tunnel | 14.10 |  | Run a ZFS Backup over the tunnel | 1. Create a 'ZFS Backup (Server-to-Server)' task and use Connect Off-Site Server to fill in the tunnel IP the same way. 2. Complete the First-time setup panel if prompted, choose the Destination Dataset, and click Create Task. 3. Run the task. | The replication completes over the tunnel and the destination dataset on the off-site server contains the replicated data.
15. Restore from Remote & Cloud Backups | 15.1 |  | Browse files from a server backup | 1. On the Remote Backups tab, connect to a server and click Restore. 2. Set the source to Server Backups and pick a backup task from the dropdown. 3. Navigate into folders, use the '..' row, and use the breadcrumb trail. Click the Name header to change the sort order. 4. Use Select All and Deselect All. | The Restore button changes to Return to Backups. Task entries show their direction - '-> host:path' for pushes and '<- host:path' for pulls. Files load for the chosen task, navigation works in both directions, and the selected-count badge matches your selection.
15. Restore from Remote & Cloud Backups | 15.2 |  | Restore files back to the server | 1. Select some files. 2. In Restore Destination, choose Restore to Server, untick 'Restore to original path', and enter a Server destination path such as /data/restored. 3. Tick 'Create folder if it doesn't exist' and start the restore. | Progress is shown as 'Restoring...' and then 'Restore Complete', and the files exist at the destination path on the server with matching contents.
15. Restore from Remote & Cloud Backups | 15.3 |  | Restore to the original path | 1. Delete or rename a file on the server. 2. Restore it with 'Restore to original path' ticked. | The file is put back exactly where it came from, with its original contents.
15. Restore from Remote & Cloud Backups | 15.4 |  | Download restored files to this computer | 1. Select files and choose Download to this Computer. 2. Click Browse and pick a Download to folder. 3. Start the restore and open the downloaded files. | The files download to the chosen folder and their contents match the originals.
15. Restore from Remote & Cloud Backups | 15.5 |  | Restore from a cloud backup | 1. In Restore, set the source to Cloud Backups and pick a cloud account. 2. Browse to a backed-up folder and select files. 3. Restore them to the server, then repeat using Download to this Computer. | Cloud files are listed, both destinations work, and the restored contents match what is in the cloud.
15. Restore from Remote & Cloud Backups | 15.6 |  | Cancel a running restore | 1. Start a restore of a large folder. 2. Click Cancel while it is running. | The restore stops promptly, the app reports that it was cancelled, and the app remains usable.
16. Snapshots - Browse, Rollback & Delete | 16.1 |  | Snapshots are listed for a dataset | 1. On the Remote Backups tab, click Snapshots. 2. Select a dataset in the Datasets panel on the left. 3. Hover any replication-anchor marker. | The dataset's snapshots are listed with readable timestamps, including the hourly, daily and weekly snapshots created when Split Pools was enabled during setup. Anchors are marked, and hovering explains which tasks depend on them.
16. Snapshots - Browse, Rollback & Delete | 16.2 |  | Browse files pulls a file out of a snapshot | 1. Pick a snapshot and click Browse files. 2. Find a file that has since been changed or deleted and restore it. 3. Check the file on the server. | The snapshot contents can be browsed and the restored file matches the version from that point in time.
16. Snapshots - Browse, Rollback & Delete | 16.3 |  | Rollback reverts a dataset to a snapshot | 1. Note the current contents of a test dataset, then add and change some files. 2. Click Rollback on a snapshot taken before those changes and confirm the warning. 3. Check the dataset contents. | A clear warning explains that every change made after the snapshot will be lost. After rollback, the dataset matches its state at the time of the snapshot.
16. Snapshots - Browse, Rollback & Delete | 16.4 |  | Delete a snapshot | 1. Click Delete on a snapshot that is NOT marked as a replication anchor. 2. Refresh the list. | The snapshot is removed from the list and the other snapshots are unaffected.
17. Dashboard Insights & Log Viewer | 17.1 |  | The status strip reflects reality | 1. Return to the Dashboard. 2. Compare the 'X Scheduled Tasks' count in the status strip to the tasks actually configured in the Backup Manager. 3. If any task has failed, confirm the 'N Failed' indicator and the 'N backup tasks failed recently.' banner appear, then click View Backups. | The counts match what is actually configured, the 'Viewing: <server name>' line names the selected server, and View Backups jumps straight to the Backup Manager.
17. Dashboard Insights & Log Viewer | 17.2 |  | Topology map draws the backup network | 1. Click Show Topology in the status strip. 2. Look for this computer, your servers, any cloud destination, and the WireShield tunnel between the two sites. 3. Click Hide Topology. | The map draws every node you have configured, including the tunnel link, and the toggle hides it again.
17. Dashboard Insights & Log Viewer | 17.3 |  | Recent Activity and Upcoming Backups populate | 1. With several backups run and scheduled, look at Recent Activity, Upcoming Backups, Last Backup and Last Restore. | Recent Activity lists the runs with green success dots, red failure dots, and a spinning icon for anything running now. Upcoming Backups shows the next scheduled runs in its week calendar, and the Last Backup and Last Restore cards name the most recent of each.
17. Dashboard Insights & Log Viewer | 17.4 |  | Log Viewer - Client Logs contain no plain-text passwords | 1. Open View Logs from the menu, or Logs from Quick Actions. 2. On the Client Logs tab, look for the connections and backups you ran earlier in this test pass. 3. Search the log for any password you typed during this test pass. 4. Click the Refresh icon in the header, then click Back. | The page is titled Log Viewer with the subtitle 'View logs from the local client app and connected servers.' Client Logs lists recent activity with timestamps. No password, token or other secret appears in readable form anywhere. Back returns you where you came from.
17. Dashboard Insights & Log Viewer | 17.5 |  | Log Viewer - Server Logs | 1. Switch to the Server Logs tab. 2. Pick a Server, set Source to 'All server logs', and click Fetch Server Logs. 3. Repeat with Source set to setup-module.log. | The button reads 'Fetching...' and then the server's log output appears. Changing Source changes which log is shown.
18. Automatic Updates | 18.1 |  | The app finds a newer version | 1. Install a build that is older than the latest published release. 2. Launch the app and leave it open for a couple of minutes. | The app notifies you that an update is available and downloading, without you having to look for it.
18. Automatic Updates | 18.2 |  | The update finishes downloading | 1. Leave the app open until the download completes. | You are told the update has been downloaded and what will happen next.
18. Automatic Updates | 18.3 |  | Update installs on quit (macOS) | 1. Once the update is downloaded, quit the app completely. 2. Launch it again and check the version shown in the window title. | The app installs the update on quit and relaunches on the new version with your saved servers and backup tasks intact.
19. Reliability & Edge Cases | 19.1 |  | Server going offline mid-operation | 1. Start a long-running remote backup. 2. Disconnect the server from the network while it runs. 3. Reconnect it and refresh the app. | The app reports the lost connection clearly instead of hanging or crashing, and it reconnects and shows accurate status once the server is back.
19. Reliability & Edge Cases | 19.2 |  | Server reboot | 1. Reboot a connected server. 2. Wait for it to come back and use the app normally. | The app shows the server as offline while it is down and reconnects afterwards without needing the app to be restarted.
19. Reliability & Edge Cases | 19.3 |  | Two backups at once | 1. Start two backup tasks so they run at the same time. | Both complete successfully, both show separate progress, and neither corrupts the other's data.
19. Reliability & Edge Cases | 19.4 |  | Large data set | 1. Back up a folder of at least 20 GB or 50,000 files. 2. Use the app normally while it runs. | The backup completes successfully and the app stays responsive throughout.
19. Reliability & Edge Cases | 19.5 |  | Leave the app running for an extended period | 1. Leave the app open with scheduled tasks for several hours or overnight. 2. Check on it the next working session. | The app is still running and responsive, scheduled backups ran on time, and status information is current.
19. Reliability & Edge Cases | 19.6 |  | Cancel setup part way through | 1. Start a server setup and go a few steps in. 2. Navigate away or close the wizard before clicking Complete Setup. 3. Return to the Dashboard and start again. | The app handles the abandoned setup cleanly, leaves the server untouched, and lets you start over without error.
19. Reliability & Edge Cases | 19.7 |  | Uninstall the app - run this last (macOS) | 1. Delete any remaining backup tasks from within the app. 2. Drag 45Drives Storage Wizard from Applications to the Trash. 3. Open Terminal and run 'crontab -l' to confirm no Houston backup jobs remain. | The app removes cleanly with no leftover scheduled backup jobs.

## Instructions
45Drives Storage Wizard - macOS Test Plan
Who this is for
You do not need to be a technical user. Every test tells you what to do and what you should see.
If what you see does not match the Expected Result, that is a failure - write down what happened instead.
How to Use This Test Plan
1. Work down the Test Plan sheet in order. The sections are deliberately sequenced so that nothing
asks you to check something that has not been created yet.
2. For each test, follow the Steps column and compare what you see to the Expected Result.
3. Enter PASS or FAIL in the Pass/Fail column.
4. If it fails, write what actually happened in Actual Result and why in Notes / Failure Reason.
5. Rate Severity: Critical / High / Medium / Low.
6. Attach a screenshot for anything that fails or looks wrong.
7. If you cannot run a test, write 'BLOCKED - depends on X.Y' in Notes and move on.
How the sections are ordered
Sections 1 and 2 only cover what you can check before any server exists - installation, the menu,
themes, and settings that persist across a restart.
Sections 3 to 5 build the servers (Simple, Custom, and Bulk).
Sections 6 to 8 check the Dashboard, saved logins, and Server Management now that servers exist.
Sections 9 to 16 cover backups and restores, which need both a server and data.
Section 17 revisits the Dashboard's topology map, activity feed, and the Log Viewer, because those
are only meaningful once real backups have run.
Naming
Every button, field, tab, and message quoted in this plan is the label shown in the app. If a label
on screen does not match the one written here, that is itself a defect - record it in Notes.
What is in scope
The desktop app on macOS, the server setup it performs, the backups and restores it drives,
and the server tools it embeds (Super Simple Setup, Task Scheduler, ZFS, WireShield).
Why rsync and ZFS replication are each tested twice
Sections 11 and 12 run each task type against a plain LAN address. Section 14 runs the same two task
types again using a WireShield tunnel address. That second pass is not a repeat: it proves the
address handed back from WireShield is usable and that SSH, routing, and transfer all work over the
WireGuard interface. Cloud backup is run once only, because it goes directly to the provider and
never uses the tunnel.
What is deliberately NOT in scope
- WireShield pairing and tunnel management as features in their own right. They are already tested.
Only the handoff between a backup task and WireShield, and backups run over the tunnel, are
covered here.
- Exhaustive option-by-option coverage of rsync, cloud, and ZFS replication tasks. These are live
and stable. One working task of each type is enough.
- Cloud provider token expiry and access revocation.
- Saved logins going stale after 30 days - this cannot be triggered within a test window (test 7.5).
Severity Definitions
Critical - The app crashes, data is lost, or something insecure happens
High - A feature is completely broken with no way around it
Medium - A feature is partly broken but there is a workaround
Low - Cosmetic or a minor annoyance
Test Environment Prerequisites
- Two 45Drives servers on the same network. At least one with 6 or more drives so Split Pools and
Enable Backup Pool can be tested.
- A third unconfigured server, or the ability to reset one, for the Custom and Bulk setup runs.
- One cloud account you sign in to (Dropbox or Google Drive) and one that uses keys
(Amazon S3, Wasabi, or Backblaze B2).
- Internet access from both servers so the two can pair over WireShield.
- Test files including a large file (1 GB+) and files with spaces and accented characters in their
names.
- A build of the app one version behind the latest release, so the update tests have something to
find.
Note on the WireShield tunnel tests
Both servers are on the same network for this test pass, so the tunnel tests exercise the local path
only. Confirm traffic really went through the tunnel by checking the connection's Received / Sent
counters before and after each backup that uses the tunnel address.
Reference
docs/45Drives_Storage_Wizard_User_Guide.md