## Summary
Field | Value
Application | 45Drives Storage Wizard
Platform Under Test | Windows
Edition | Technical
Tester
Date
Build / Version
OS Version
Server(s) Under Test
Network Environment
Total Tests | 96
Passed
Failed
Blocked / Skipped
Overall Result
Section | Test Count
1. Installation & First Launch | 4
2. Dashboard | 4
3. Menu, Themes & Settings | 4
4. Set Up a Single Server - Simple Path | 9
5. Set Up a Single Server - Custom Path | 7
6. Set Up Multiple Servers (Bulk) | 4
7. Server Management | 5
8. Manage Connections (Saved Credentials) | 4
9. Back Up This Computer to the Server | 11
10. Restore from a Local Backup | 3
11. Remote Backups - Server to Server (Rsync) | 5
12. Remote Backups - ZFS Replication | 3
13. Cloud Accounts & Server to Cloud Backup | 5
14. Off-Site Backups Over a WireShield Tunnel | 8
15. Restore from Remote & Cloud Backups | 6
16. Snapshots - Browse, Restore & Rollback | 4
17. Automatic Updates | 3
18. Reliability & Edge Cases | 7

## Test Plan
Section | ID | Pass/Fail | Test Case | Steps | Expected Result | Actual Result | Notes / Failure Reason | Severity | Screenshot/Evidence
1. Installation & First Launch | 1.1 |  | Install the app on Windows | 1. Run the 45Drives Storage Wizard installer (.exe). 2. If Windows SmartScreen warns about the publisher, note it in the Notes column and choose Run anyway. 3. Accept the default install location, or change it if offered. 4. Finish the installer and launch the app from the Start Menu shortcut. Technical verification: 5. Right-click the installed .exe, open Properties > Digital Signatures, and check the signing certificate. 6. Confirm the install landed in the per-user location unless you changed it. | The installer completes without errors. A '45Drives Storage Wizard' shortcut exists in the Start Menu and the app opens to the Dashboard. Technical verification: The binary carries a valid 45Drives code signature and the installer honours a custom install directory.
1. Installation & First Launch | 1.2 |  | First launch shows a usable empty state | 1. Launch the app on a machine that has never run it before. 2. Look at the Dashboard. | The Dashboard loads with no saved servers and gives a clear next step (for example a Set Up a Server quick action). Nothing is blank, broken, or stuck loading.
1. Installation & First Launch | 1.3 |  | Server discovery works through the Windows firewall | 1. Power on an unconfigured 45Drives server on the same network. 2. Launch the app and start the setup wizard. 3. If Windows Firewall prompts for network access, allow it on Private networks. Technical verification: 4. Open Windows Defender Firewall > Advanced Settings and confirm an inbound rule exists for the app. 5. Temporarily block UDP 5353 and retry discovery. | The server appears in the discovered server list within about a minute. Technical verification: Discovery uses mDNS over UDP 5353. With it blocked the app must show a clear message and offer manual entry rather than an empty list.
1. Installation & First Launch | 1.4 |  | Settings and saved servers survive a restart | 1. Complete at least one server setup so the Dashboard lists a saved server. 2. Quit the app completely. 3. Launch it again. Technical verification: 4. Inspect the app's userData directory (Windows %APPDATA%, macOS ~/Library/Application Support, Linux ~/.config) and confirm settings and saved-server state are written there. | The saved server, its name, and your settings are all still there. Technical verification: All persisted state lives under the app's own userData directory. Nothing is written outside it.
2. Dashboard | 2.1 |  | Saved server shows correct live status | 1. From the Dashboard, look at the Saved Servers list with a configured server powered on. 2. Power the server off (or unplug its network cable) and wait for the Dashboard to refresh. 3. Power it back on. | The server shows a green/online indicator when reachable, changes to grey/offline when it is not, and returns to online once it is back.
2. Dashboard | 2.2 |  | Status strip reflects reality | 1. Note the counts shown in the Dashboard status strip. 2. Compare them to what actually exists: saved servers, backup tasks, and tunnels. | The counts match what is actually configured.
2. Dashboard | 2.3 |  | Quick Actions open the right destinations | 1. Click each Quick Action on the Dashboard in turn, returning to the Dashboard between each. | Each action opens its intended screen (setup wizard, bulk setup, backup manager, etc.) with no dead buttons or error screens.
2. Dashboard | 2.4 |  | Topology map and activity feed populate | 1. With at least one saved server, and after running at least one backup, return to the Dashboard. | The topology map shows the server (and any tunnel), Recent Activity lists the backup that ran, and Upcoming Backups lists the next scheduled run.
3. Menu, Themes & Settings | 3.1 |  | Theme change applies and persists | 1. Open the menu and switch the theme (light / dark / system). 2. Visit the Dashboard, Backup Manager, and a server setup screen. 3. Quit and relaunch the app. | The whole app follows the chosen theme with readable text everywhere, and the choice is remembered after restart.
3. Menu, Themes & Settings | 3.2 |  | A settings change takes effect and persists | 1. Open Settings and change a setting that has visible behaviour (for example Auto-connect favorites). 2. Save, quit, and relaunch the app. 3. Exercise the behaviour the setting controls. | The setting is still set after restart and the app behaves according to it.
3. Menu, Themes & Settings | 3.3 |  | Reset settings to defaults | 1. Change two or three settings. 2. Use the reset-to-defaults option in the Settings footer. 3. Confirm. | All settings return to their default values and the app keeps working normally.
3. Menu, Themes & Settings | 3.4 |  | Logs are viewable and contain no plain-text passwords | 1. Perform an action that logs activity (connect to a server, run a backup). 2. Open the log viewer from the menu. 3. Search the log for any password you typed. Technical verification: 4. Also search the log files on disk under the app's userData/logs directory for the password, any SSH key passphrase, and any cloud secret you entered. | Recent activity is listed with timestamps. No password appears in readable form anywhere in the log. Technical verification: No credential of any kind appears in readable form in the on-disk logs. Secrets are redacted or absent.
4. Set Up a Single Server - Simple Path | 4.1 |  | Walk the setup wizard to server discovery | 1. Start Set Up a Server from Quick Actions. 2. Move forward through the introduction/hardware steps to the discovery screen. | Every step advances cleanly with working Back/Next, and the discovery screen lists your unconfigured server with its name and IP.
4. Set Up a Single Server - Simple Path | 4.2 |  | Connect to the discovered server | 1. Select the discovered server. 2. Enter the server login when prompted. 3. First enter a deliberately wrong password, then the correct one. Technical verification: 4. On the server, watch the auth log during both attempts: journalctl -fu sshd (or tail -f /var/log/secure). | The wrong password is rejected with a clear message and no crash. The correct password loads the Super Simple Setup 'Set Up Your Server' screen inside the app window. Technical verification: The failed attempt is logged as an SSH auth failure and surfaced in the app as an auth error, not a generic one. The successful attempt loads the cockpit-super-simple-setup page in the embedded webview over port 9090.
4. Set Up a Single Server - Simple Path | 4.3 |  | Credential fields reject invalid input | 1. On the Simple credentials step, try each of these in turn: a server name with a space, a username of 'root', a password of 'password', and mismatched Confirm Password. | Each invalid entry is blocked with a clear, plain-English message, and Next stays disabled until the entry is fixed.
4. Set Up a Single Server - Simple Path | 4.4 |  | Complete the credentials step | 1. Enter a valid server name, username, strong password, and network folder name. 2. Check the folder preview line. 3. Click Next and read the save-your-credentials confirmation. 4. Choose OK, Proceed. | The folder preview shows the share path that will be created. The confirmation dialog appears warning you to record the credentials, and proceeding moves to the drive step.
4. Set Up a Single Server - Simple Path | 4.5 |  | Drive step shows the real hardware | 1. On the Storage Drive Summary step, review the drive view and the Issues panel. 2. Click an individual drive. 3. Physically remove a drive, wait for the view to refresh, then reseat it. | The drive count matches the physical server. Clicking a drive shows its model, serial, capacity and health. Removing a drive raises an issue and blocks Next; reseating it clears the issue.
4. Set Up a Single Server - Simple Path | 4.6 |  | Wipe drives that contain old data | 1. Using a server whose drives contain previous partitions, confirm the Wipe all drives option appears. 2. Open Change method and choose Quick wipe. 3. Continue with the setup. | The wipe option is offered with a clear description of each method, Quick wipe is selected, and the wipe runs as part of the setup without failing.
4. Set Up a Single Server - Simple Path | 4.7 |  | Split Pools (Active Backup) | 1. On a server with 6 or more drives, tick Split Pools. 2. Review the capacity table. 3. If a server with fewer than 6 drives is available, confirm the option is unavailable there. Technical verification: 4. After setup completes, on the server run: zfs list -t snapshot ¦ head, and open Cockpit > Task Scheduler. | With 6+ drives the option enables and the capacity table shows a Storage row and a Backup row with failure tolerance and usable space. With fewer than 6 drives the option is disabled and explains why. Technical verification: Two pools exist. Hourly, daily and weekly snapshot tasks are scheduled with 1 day / 1 week / 1 month retention, plus a weekly scrub task.
4. Set Up a Single Server - Simple Path | 4.8 |  | Review the summary and apply the configuration | 1. Check the Summary step against what you entered. 2. Reveal the hidden password with the eye icon. 3. Click Complete Setup and watch the progress checklist through to the end. Technical verification: 4. On the server, follow the setup output with: journalctl -f 5. Afterwards confirm the installed packages: cockpit, cockpit-super-simple-setup, cockpit-scheduler, cockpit-zfs, wireshield, houston-broadcaster, samba, zfs, rsync, rclone, wireguard-tools. 6. Confirm the firewall opened 9090/tcp, 9095/tcp and 5353/udp (firewall-cmd --list-all or ufw status). | The summary matches your input. Every checklist step turns green with no failures. If the server name was changed, the server reboots and the app explains that this is expected. Technical verification: Every expected package is installed and all three ports are open. No step in the checklist silently skipped.
4. Set Up a Single Server - Simple Path | 4.9 |  | Verify the finished server | 1. After setup completes, return to the Dashboard. 2. Open the new network folder from this computer's file browser using the share path and the credentials you created. 3. Copy a test file into it. Technical verification: 4. On the server run: zpool status and zfs list 5. Run: smbclient -L //localhost -U <your user> 6. Browse to https://<server>:9090 and confirm Cockpit loads. | The server is listed as configured and online. The share opens with your credentials and accepts the test file. Technical verification: The pool is ONLINE with the expected vdev layout, the dataset exists, the share is exported, and Cockpit is reachable.
5. Set Up a Single Server - Custom Path | 5.1 |  | Server Info step | 1. On a fresh unconfigured server, choose CUSTOM. 2. Fill in server name, admin username and password. 3. Set a timezone and leave Disable Root SSH and Sync Time via NTP enabled. | All fields validate the same way as the Simple path and Next advances to the ZFS step.
5. Set Up a Single Server - Custom Path | 5.2 |  | ZFS configuration with a chosen RAID level | 1. Pick a RAID level (for example raidz2). 2. Select fewer drives than the minimum, then enough drives. 3. Change the pool name and set compression, then set a dataset name. Technical verification: 4. After the setup completes, confirm the layout: zpool status <pool> 5. Confirm dataset properties: zfs get compression,recordsize,atime,casesensitivity <pool>/<dataset> | The heading tracks how many drives are selected against the minimum. Next is blocked below the minimum and enabled once satisfied. Pool and dataset options accept the changes. Technical verification: The vdev type matches the RAID level chosen in the wizard and every dataset property matches what you set.
5. Set Up a Single Server - Custom Path | 5.3 |  | Enable Backup Pool and assign drives | 1. On a server with 6 or more drives, tick Enable Backup Pool. 2. Assign drives to Storage and Backup using the Pool column. 3. Configure the backup pool options. | The Pool column appears, drives can be assigned to either pool, and a matching Backup pool configuration section is shown.
5. Set Up a Single Server - Custom Path | 5.4 |  | Add a group and an extra user | 1. On Users & Groups, add a group. 2. Add a second user, give it a password, and tick the new group. 3. Try to add a user with a name that already exists. | The admin user is shown automatically with an Admin badge. The new group and user are accepted. A duplicate or reserved username is rejected with a clear message.
5. Set Up a Single Server - Custom Path | 5.5 |  | Add a second Samba share with restricted access | 1. On Samba Shares, confirm the primary share name is locked. 2. Add a second share with its own path. 3. Untick All users and grant access to only the extra user you created. | The primary share cannot be renamed. The second share is added and access is limited to the chosen user.
5. Set Up a Single Server - Custom Path | 5.6 |  | Apply the custom configuration | 1. Review the Custom Summary, expanding the drive and pool panels. 2. Click Complete Setup and watch the checklist finish. | The summary matches everything you configured and every step completes green.
5. Set Up a Single Server - Custom Path | 5.7 |  | Verify the custom result on the server | 1. Open the finished server's management page. 2. Check the storage pool name and RAID level, the users and groups, and both Samba shares. 3. From this computer, open the second share using the extra user's credentials, then try it with a user that should not have access. Technical verification: 4. On the server run: getent passwd <extra user>, getent group <new group>, testparm -s, and sshd -T ¦ grep -i permitrootlogin | Everything on the server matches the custom configuration. The permitted user can open the second share; the non-permitted user is refused. Technical verification: The user and group exist with the expected membership, both share definitions appear in testparm with the correct valid users, and root SSH login is disabled.
6. Set Up Multiple Servers (Bulk) | 6.1 |  | Configure a bulk deployment | 1. Open Setup Multiple Servers from Quick Actions. 2. Add a card for each of two unconfigured servers. 3. Fill in Global Defaults (SSH and SMB credentials) and click Apply to all servers missing values. 4. Fill in whatever differs per server. | Both cards are added, the defaults populate every blank field on both cards, and per-server edits are preserved.
6. Set Up Multiple Servers (Bulk) | 6.2 |  | Export and import a bulk template | 1. Click Export Template and save the file. 2. Clear or restart the bulk setup screen. 3. Click Import Template and load the saved file. Technical verification: 4. Open the exported JSON in a text editor and inspect it. | The exported file is created and importing it restores the same server cards and values. Technical verification: The file is valid JSON, round-trips without loss, and contains no plain-text passwords unless that behaviour is explicitly documented.
6. Set Up Multiple Servers (Bulk) | 6.3 |  | Run the bulk deployment | 1. Start the deployment. 2. Watch the progress bar at the bottom. 3. Wait for it to finish. Technical verification: 4. Run the deployment a second time with Parallel mode enabled. | The action bar shows which server is running and the done count increases. Both servers finish successfully and appear as configured servers on the Dashboard. Technical verification: Both modes complete successfully. Parallel mode is measurably faster and per-server progress and errors stay correctly attributed to the right server.
6. Set Up Multiple Servers (Bulk) | 6.4 |  | One server failing does not stop the others | 1. Set up two server cards, giving one card a deliberately wrong SSH password. 2. Run the deployment. | The bad card is reported as failed with a clear reason. The other server still completes successfully.
7. Server Management | 7.1 |  | Open the management page and read its status | 1. From the Dashboard, hover a saved server and click the gear icon (or double-click the row). 2. Check the header. | The management page opens showing the server name, user@host and IP, and a green status dot while the server is online.
7. Server Management | 7.2 |  | All management tabs load real data | 1. Visit each tab in turn: Connection, Network, Storage, Users & Groups, Samba, System. | Every tab loads without an error or endless spinner and shows information that matches the server you configured.
7. Server Management | 7.3 |  | Make a change using staged changes | 1. On the Users & Groups or Samba tab, make a change (for example add a user or a share). 2. Confirm the change is listed as staged rather than applied immediately. 3. Apply the staged changes. 4. Reload the page. Technical verification: 5. Confirm the change reached the real system config, not just the UI: getent passwd / getent group for a user change, or testparm -s for a share change. | The change is held as pending until applied, applying it succeeds, and after reloading the change is present on the server. Technical verification: The applied change is present in the server's actual configuration files.
7. Server Management | 7.4 |  | Discard staged changes | 1. Stage a change. 2. Discard it instead of applying. 3. Reload the page. | The change is dropped and the server is unchanged.
7. Server Management | 7.5 |  | Offline server is handled gracefully | 1. Open a saved server's management page while that server is powered off. | The app shows a clear offline/unreachable message. It does not hang, crash, or show a raw technical error.
8. Manage Connections (Saved Credentials) | 8.1 |  | Saved connections are listed | 1. After setting up a server and connecting to it, open Manage Connections. | The server is listed with its saved username, and no password is displayed in readable form.
8. Manage Connections (Saved Credentials) | 8.2 |  | Credentials are remembered after a restart (Windows) | 1. Connect to a server and let the app save the credentials. 2. Quit and relaunch the app. 3. Connect to the same server again. Technical verification: 4. Search the app's userData directory for the password string to confirm it is not stored in the clear. | The app connects without asking you to re-enter the password. Technical verification: The credential is stored through Electron safeStorage (DPAPI) and is not recoverable in plain text from disk.
8. Manage Connections (Saved Credentials) | 8.3 |  | Forget a saved connection | 1. Remove/forget a saved connection from Manage Connections. 2. Connect to that server again. | The entry disappears from the list and the app asks for the password again on the next connection.
8. Manage Connections (Saved Credentials) | 8.4 |  | Stale credential expiry - NOT TESTED | This behaviour (credentials older than 30 days being treated as stale) cannot be exercised within a normal test window. Mark this row as SKIPPED and take no action. | N/A - deliberately out of scope for this test pass.
9. Back Up This Computer to the Server | 9.1 |  | Create a local backup task | 1. Open the Backup Manager, Local Backups tab, and click New Backup. 2. Choose the destination network folder for your server (use the refresh icon if it is not listed). 3. Leave Schedule Type on Simple and choose Hourly. 4. Add two folders containing test files. 5. Give each a friendly name and continue. | The share is listed and selectable, both folders are added, and Next is only enabled once at least one folder is chosen.
9. Back Up This Computer to the Server | 9.2 |  | Overlapping folder selections are blocked | 1. In the folder list, add a folder. 2. Try to add the same folder again. 3. Try to add a subfolder of it, then a parent of it. | Each attempt is refused with a plain message explaining the conflict (already added / subfolder already added / parent already added).
9. Back Up This Computer to the Server | 9.3 |  | Samba login step | 1. On the Samba Login step, enter a deliberately wrong password and continue. 2. Then enter the correct username and password you created during setup. | The wrong credentials are rejected with 'Invalid credentials'. The correct credentials are accepted and the wizard moves to the Summary.
9. Back Up This Computer to the Server | 9.4 |  | Finish the wizard and confirm the task | 1. Complete the wizard through to the confirmation screen. 2. Use the button to go to the Backup Manager. Technical verification: 3. In PowerShell run: Get-ScheduledTask -TaskName 'Houston_Backup_Task_*' 4. Confirm the generated .bat exists under %LOCALAPPDATA%\houston-backups\scripts and the credential file under %LOCALAPPDATA%\houston-backups\credentials. | The confirmation screen appears and the new task is listed with the correct name, user, source, destination, frequency and next run time. Technical verification: A Windows Scheduled Task exists with the trigger you chose, and its script and credential file are present.
9. Back Up This Computer to the Server | 9.5 |  | Run a backup immediately | 1. Select the task and click Run Now. 2. Watch the progress panel at the bottom. 3. When it finishes, open the network folder on the server from this computer's file browser. Technical verification: 4. Confirm the destination UNC path is reachable, then list any remaining differences: robocopy <source> \\<server>\<share>\<path> /L /E /NJH /NJS | Progress is shown while it runs, the task reports success, and every file from the source folders is present on the server with matching contents. Technical verification: robocopy in list-only mode reports nothing left to copy, confirming a complete transfer.
9. Back Up This Computer to the Server | 9.6 |  | A scheduled backup runs on its own | 1. Leave the hourly task in place and add a new file to one of the source folders. 2. Wait for the scheduled time to pass without touching the app. 3. Check the task's Last Run and the server folder. | The backup runs automatically at the scheduled time and the new file appears on the server.
9. Back Up This Computer to the Server | 9.7 |  | Scheduled backup still runs with the app closed | 1. With a scheduled task in place, quit the app completely. 2. Wait for the next scheduled run to pass. 3. Relaunch the app and check the task's Last Run, then check the server folder. Technical verification: 4. In Task Scheduler, check the task's Last Run Time and Last Run Result. | The backup ran while the app was closed and the files reached the server. Technical verification: Last Run Result is 0x0 and the run happened while the app was not running.
9. Back Up This Computer to the Server | 9.8 |  | Edit, disable, and delete a task | 1. Select a task and click Edit; change its name and schedule, then save. 2. Turn the Enabled toggle off and wait past the next scheduled time. 3. Turn it back on, then delete the task. Technical verification: 4. After deleting, confirm the Houston_Backup_Task_* entry is gone: Get-ScheduledTask -TaskName 'Houston_Backup_Task_*' 5. Confirm the generated .bat and credential file were removed. | The edits are saved and shown in the list. While disabled the task does not run. Deleting removes it from the list, and it does not run again afterwards. Technical verification: No orphaned scheduled task, script, or credential file is left behind.
9. Back Up This Computer to the Server | 9.9 |  | Task logs are readable | 1. Select a task that has run and click Logs. | The run history is shown with timestamps and a clear success or failure result for each run.
9. Back Up This Computer to the Server | 9.10 |  | Backup handles awkward files | 1. Add files to a source folder with: a long name, accented and non-English characters, spaces, and a file over 1 GB. 2. Run the backup. Technical verification: 3. Also include a file with a character that is illegal on SMB (for example a colon) and a path close to the platform maximum length. | All files are copied with their names intact and the large file transfers completely without corrupting the run. Technical verification: Illegal or over-long names are reported per file with a clear reason, and the rest of the backup still completes rather than aborting the whole run.
9. Back Up This Computer to the Server | 9.11 |  | Backup fails clearly when the server is unreachable | 1. Power off the server (or disconnect it from the network). 2. Run the backup task. 3. Bring the server back and run it again. Technical verification: 4. Open the task log and read the underlying error. | The task reports a clear failure explaining that the server could not be reached, the app stays usable, and the next run succeeds once the server is back. Technical verification: The log records an actionable error (mount failure or host unreachable) with a non-zero exit status, and the task is marked failed rather than left stuck in a running state.
10. Restore from a Local Backup | 10.1 |  | Browse a local backup | 1. Select a completed local backup task and click View/Restore. 2. Navigate into subfolders and back out again. | The backed-up folder structure is shown and navigation works in both directions.
10. Restore from a Local Backup | 10.2 |  | Restore a single file to this computer | 1. Delete or rename a file in the original source folder. 2. In the backup browser, select that file and restore it. 3. Open the restored file. Technical verification: 4. Compare the restored file to the copy on the share: certutil -hashfile <restored> SHA256 and the same for the source. | The file is restored to this computer and its contents are identical to the original. Technical verification: The hashes match. Note that restores on Windows use robocopy.
10. Restore from a Local Backup | 10.3 |  | Restore a whole folder to this computer | 1. Select an entire backed-up folder and restore it. | Every file and subfolder is restored with the correct structure and contents.
11. Remote Backups - Server to Server (Rsync) | 11.1 |  | Connect to a server | 1. On the Remote Backups tab, choose your server from Select Server. 2. Click Connect and enter a deliberately wrong password. 3. Enter the correct password. Technical verification: 4. On the server, watch the auth log during both attempts: journalctl -fu sshd | The wrong password is rejected with a clear message. The correct password connects and the server's backup task list loads. Technical verification: The failed and successful authentications are both visible server-side, and the app surfaces the real reason for the failure.
11. Remote Backups - Server to Server (Rsync) | 11.2 |  | Connect using an SSH key | 1. Disconnect, then Connect again. 2. Tick Authenticate with SSH private key, browse to a valid key, and supply the passphrase if it has one. Technical verification: 3. Confirm the key the app manages lives under the app's userData/.ssh directory. 4. Confirm the matching public key is present in the server account's ~/.ssh/authorized_keys. | The app connects successfully using the key. Technical verification: Key authentication succeeds with no password prompt and the app did not copy the private key anywhere outside its own data directory.
11. Remote Backups - Server to Server (Rsync) | 11.3 |  | Create a server-to-server file copy task | 1. Click New Backup and give the task a name. 2. Choose the File Copy / Sync (Rsync) template. 3. Pick a source folder from the dropdown of folders already backed up from this computer. 4. Enter the second server's address, user and password, then click Test Connection (SSH). 5. Set a target path, choose a schedule, and click Create Task. Technical verification: 6. On the server, confirm the task was persisted by cockpit-scheduler (open Cockpit > Task Scheduler, or inspect the scheduler's task definitions). | The source dropdown lists the client-backed-up folders, Test Connection reports success, and the task is created and appears in the list as Server-to-Server. Technical verification: The task exists server-side and remains after the desktop app disconnects, confirming it is not client-driven.
11. Remote Backups - Server to Server (Rsync) | 11.4 |  | Run the file copy task and verify the data | 1. Select the new task and run it. 2. Watch its status while it runs. 3. When it completes, check the target path on the destination server. Technical verification: 4. On the destination server, confirm nothing is left to transfer: rsync -avnc <source path>/ <dest path>/ 5. Check the task log for the rsync exit code. | The status shows it running and then succeeds. All files are present on the destination server with matching contents. Technical verification: rsync exits 0 and the dry-run comparison reports no remaining differences.
11. Remote Backups - Server to Server (Rsync) | 11.5 |  | Disconnect and forget a remote server | 1. Click Disconnect. 2. Click Forget for that server, then connect to it again. | Disconnect returns to the not-connected state. After Forget, the app asks for credentials again on the next connection.
12. Remote Backups - ZFS Replication | 12.1 |  | Create a ZFS replication task | 1. Click New Backup, name the task, and choose the ZFS Backup (Server-to-Server) template. 2. Pick the source pool and dataset on this server. 3. Enter the destination server address, user and port, and pick the destination dataset. 4. Click Test Connection (SSH), set a schedule, and create the task. Technical verification: 5. From the source server, confirm passwordless SSH to the destination works: ssh -p <port> <user>@<dest> zfs list | The pool and dataset dropdowns populate from the real server, Test Connection succeeds, and the task is created and listed as ZFS to ZFS Backup. Technical verification: The key exchange is in place and zfs on the destination is reachable over SSH without a password prompt.
12. Remote Backups - ZFS Replication | 12.2 |  | Run the replication and verify it | 1. Run the task. 2. When it finishes, check the destination server's dataset. Technical verification: 3. On the destination run: zfs list -t snapshot -r <destination dataset> 4. Compare properties: zfs get -r compression,recordsize <destination dataset> | The task succeeds and the destination dataset contains the replicated data and a matching snapshot. Technical verification: The destination holds a snapshot matching the source and dataset properties are preserved through the replication.
12. Remote Backups - ZFS Replication | 12.3 |  | Second run sends only the changes | 1. Add a file to the source dataset. 2. Run the task again. 3. Compare how long it takes against the first run and check the destination. Technical verification: 4. Check the task log for the send invocation and the byte count. | The second run is noticeably faster than the first, completes successfully, and the new file appears on the destination. Technical verification: The second run uses an incremental send (zfs send -i or -I) anchored on the previous snapshot and moves far less data than the first.
13. Cloud Accounts & Server to Cloud Backup | 13.1 |  | Add a cloud account by signing in | 1. Open Cloud Accounts and add an account for a sign-in provider (Dropbox or Google Drive). 2. Complete the sign-in in the browser window that opens. | The sign-in completes and the account is saved and listed with the correct provider.
13. Cloud Accounts & Server to Cloud Backup | 13.2 |  | Add a cloud account using keys | 1. Add an account for a key-based provider (Amazon S3, Wasabi, or Backblaze B2). 2. Enter the access key, secret, and any required region or endpoint. 3. Save. Technical verification: 4. On the server, confirm the remote was written to the rclone configuration and works: rclone lsd <remote>: 5. Check the permissions on the rclone config file. | The account is saved and listed. If the keys are wrong, the app reports the problem clearly rather than saving a broken account. Technical verification: rclone can enumerate the remote and the config holding the secret is not world-readable.
13. Cloud Accounts & Server to Cloud Backup | 13.3 |  | Edit and remove a cloud account | 1. Rename a saved cloud account and save. 2. Remove a cloud account you no longer need. | The rename is reflected everywhere the account is offered. Removal takes it out of the list and it is no longer selectable in a backup task.
13. Cloud Accounts & Server to Cloud Backup | 13.4 |  | Create a server-to-cloud backup task | 1. Click New Backup, name the task, and choose the Cloud Backup template. 2. Pick a local folder on the server. 3. Select a saved cloud account. 4. Choose Copy as the transfer method and enter a cloud destination folder. 5. Set a schedule and create the task. Technical verification: 6. Note which rclone operation each transfer mode maps to (copy / sync / move). | The task is created and appears in the list as Cloud Backup with the correct source and destination. Technical verification: Copy mode must not delete anything at the destination. The warning about Sync and Move deleting data is shown before either is selected.
13. Cloud Accounts & Server to Cloud Backup | 13.5 |  | Run the cloud backup and verify it | 1. Run the task. 2. When it finishes, sign in to the cloud provider directly and look in the destination folder. Technical verification: 3. On the server run: rclone check <local path> <remote>:<cloud path> | The task succeeds and all files are present in the cloud folder with matching contents. Technical verification: rclone check reports zero differences.
14. Off-Site Backups Over a WireShield Tunnel | 14.1 |  | Open WireShield from a backup task | 1. Start a new remote backup task using the File Copy / Sync (Rsync) template. 2. Fill in the task name and source folder. 3. Click Connect Off-Site Server in the destination card. | WireShield opens inside the app showing the 'Pick the off-site server you want to back up to' banner, so it is clear you are choosing a destination for the task in progress.
14. Off-Site Backups Over a WireShield Tunnel | 14.2 |  | Pair the two servers from this entry point | 1. In WireShield, create a new connection on one server and generate the pairing code. 2. On the second server, join using that code. 3. Wait for the connection to show as connected. Technical verification: 4. On both servers run: wg show and ip -br a 5. Confirm the UDP port in use is 51820 or the next free port upward. | The two servers pair successfully and the connection is listed as active with both peers shown. Technical verification: Each server has a WireGuard interface with a /24 address from the 10.45.0.0/16 range (creator .1, joiner .2), a peer entry for the other server, and a recent handshake.
14. Off-Site Backups Over a WireShield Tunnel | 14.3 |  | Hand the tunnel address back to the task with Use This Connection | 1. With the selection banner showing, click Use This Connection on the paired connection row. Technical verification: 2. Check the exact value placed in the remote server address field. | The app returns to the Backup Manager, your in-progress task is restored exactly as you left it, and the remote server address is filled in with the tunnel IP automatically. Technical verification: The field contains the peer's 10.45.x.x tunnel address, not its LAN address.
14. Off-Site Backups Over a WireShield Tunnel | 14.4 |  | Hand back by picking a specific peer | 1. Repeat the previous test, but this time expand the connection row and click the specific peer server (shown with a Use hint). | The same handoff happens and the address filled into the task matches the tunnel IP of the peer you chose.
14. Off-Site Backups Over a WireShield Tunnel | 14.5 |  | Leaving WireShield without choosing does not lose the task | 1. Open WireShield from a part-filled task again. 2. Navigate back without selecting a connection. | You are returned to the task with everything you had already entered still intact and the remote address unchanged.
14. Off-Site Backups Over a WireShield Tunnel | 14.6 |  | First-time SSH setup over the tunnel | 1. With the tunnel address filled in, enter the destination server's user. 2. When the first-time setup panel asks for that account's password, supply it. 3. Click Test Connection (SSH). Technical verification: 4. Confirm the source server's public key was appended to the destination's ~/.ssh/authorized_keys. 5. From the source server run: ssh <user>@10.45.x.x true | The one-time key exchange completes, the warning about SSH login not being configured clears, and Test Connection reports success. Technical verification: Key-based SSH over the tunnel succeeds with no password prompt, and the key exchange happened once rather than on every connection.
14. Off-Site Backups Over a WireShield Tunnel | 14.7 |  | Run a file copy backup over the tunnel | 1. Finish and save the Rsync task that uses the tunnel address. 2. Note the tunnel's sent/received counters in WireShield. 3. Run the task and wait for it to finish. 4. Check the counters again and check the destination server. Technical verification: 5. Capture the tunnel counters before and after: wg show <interface> transfer 6. Confirm the destination path was reached via the tunnel address, not the LAN address. | The task succeeds, the files arrive on the destination server, and the tunnel counters increase, showing the transfer went through the tunnel. Technical verification: The transfer counters increase by roughly the volume of data copied, proving the traffic traversed the tunnel rather than taking the direct LAN path.
14. Off-Site Backups Over a WireShield Tunnel | 14.8 |  | Run a ZFS replication over the tunnel | 1. Create a ZFS Backup task and use Connect Off-Site Server to fill in the tunnel address the same way. 2. Complete the SSH setup if prompted, pick the destination dataset, and save. 3. Run the task. Technical verification: 4. On the destination run: zfs list -t snapshot -r <destination dataset> 5. Check wg show <interface> transfer again. | The replication completes over the tunnel and the destination dataset on the off-site server contains the replicated data. Technical verification: The replication lands on the destination and the tunnel counters reflect the volume replicated.
15. Restore from Remote & Cloud Backups | 15.1 |  | Browse files from a server backup | 1. On the Remote Backups tab, connect to a server and click Restore. 2. Choose Server Backups as the source and pick a backup task. 3. Navigate into folders, use the .. row, and use the breadcrumb trail. 4. Use Select All and Deselect All. | The button changes to Return to Backups, files load for the chosen task, navigation works in both directions, and the selected-count badge matches your selection.
15. Restore from Remote & Cloud Backups | 15.2 |  | Restore files back to the server | 1. Select some files. 2. Choose Restore to Server, untick Restore to original path, and enter a destination such as /data/restored. 3. Tick Create folder if it doesn't exist and start the restore. Technical verification: 4. Repeat with Create as ZFS dataset ticked and a parent dataset such as tank/data, then confirm: zfs list | Progress is shown, the restore reports Restore Complete, and the files exist at the destination path on the server with matching contents. Technical verification: A new dataset is created under the specified parent and the files are restored into it with the correct ownership and permissions.
15. Restore from Remote & Cloud Backups | 15.3 |  | Restore to the original location | 1. Delete or rename a file on the server. 2. Restore it with Restore to original path ticked. | The file is put back exactly where it came from with its original contents.
15. Restore from Remote & Cloud Backups | 15.4 |  | Download restored files to this computer | 1. Select files, choose Download to this Computer, and browse to a local folder. 2. Start the restore and open the downloaded files. Technical verification: 3. Compare checksums between the downloaded copies and the files on the server. | The files download to the chosen folder and their contents match the originals. Technical verification: Checksums match on every file.
15. Restore from Remote & Cloud Backups | 15.5 |  | Restore from a cloud backup | 1. In Restore, choose Cloud Backups as the source and pick a cloud account. 2. Browse to a backed-up folder and select files. 3. Restore them to the server, then repeat and download them to this computer. | Cloud files are listed, both destinations work, and the restored contents match what is in the cloud.
15. Restore from Remote & Cloud Backups | 15.6 |  | Cancel a running restore | 1. Start a restore of a large folder. 2. Click Cancel while it is running. | The restore stops promptly, the app reports that it was cancelled, and the app remains usable.
16. Snapshots - Browse, Restore & Rollback | 16.1 |  | Snapshots are listed for a dataset | 1. On the Remote Backups tab, click Snapshots. 2. Select a dataset from the left panel. Technical verification: 3. Cross-check the list against the server: zfs list -t snapshot -r <pool> | The dataset's snapshots are listed with readable timestamps. Snapshots used as replication anchors are marked, and hovering the marker explains which tasks depend on them. Technical verification: The UI list matches the server exactly, and the anchor markers correspond to the snapshots actually referenced by replication tasks.
16. Snapshots - Browse, Restore & Rollback | 16.2 |  | Restore a file out of a snapshot | 1. Pick a snapshot and choose Browse files. 2. Find a file that has since been changed or deleted and restore it. 3. Check the file on the server. | The snapshot contents can be browsed and the restored file matches the version from that point in time.
16. Snapshots - Browse, Restore & Rollback | 16.3 |  | Roll a dataset back to a snapshot | 1. Note the current contents of a test dataset, then add and change some files. 2. Choose Rollback on a snapshot taken before those changes and confirm the warning. 3. Check the dataset contents. Technical verification: 4. Afterwards confirm: zfs list -t snapshot -r <dataset> | A clear warning explains that later changes will be lost. After rollback, the dataset matches its state at the time of the snapshot. Technical verification: Snapshots newer than the rollback target were destroyed, as ZFS requires, and the app warned about this before proceeding.
16. Snapshots - Browse, Restore & Rollback | 16.4 |  | Delete a snapshot | 1. Delete a snapshot that is NOT marked as a replication anchor. 2. Refresh the list. Technical verification: 3. Then attempt to delete a snapshot that IS marked as a replication anchor. | The snapshot is removed from the list and other snapshots are unaffected. Technical verification: The app either blocks deleting an anchor or warns clearly that the next replication will have to send everything from scratch.
17. Automatic Updates | 17.1 |  | The app finds a newer version | 1. Install a build that is older than the latest published release. 2. Launch the app and leave it open for a couple of minutes. Technical verification: 3. Check the app log for the update check, and confirm it fires roughly five seconds after startup. 4. Confirm a development/unpackaged build does not check for updates at all. | The app notifies you that an update is available and downloading, without you having to look for it. Technical verification: The check runs automatically shortly after launch against the GitHub release feed, pre-releases are never offered, and updates are suppressed for dev builds.
17. Automatic Updates | 17.2 |  | The update finishes downloading | 1. Leave the app open until the download completes. | You are told the update has been downloaded and what will happen next.
17. Automatic Updates | 17.3 |  | Update installs on quit (Windows) | 1. Once the update is downloaded, quit the app completely. 2. Launch it again and check the version shown in the app. Technical verification: 3. Check the app log for the download and the install-on-quit handoff. | The app installs the update on quit and relaunches on the new version with your servers and tasks intact. Technical verification: electron-updater downloads automatically and installs on quit. User data, saved servers, and scheduled tasks all survive the upgrade.
18. Reliability & Edge Cases | 18.1 |  | Server going offline mid-operation | 1. Start a long-running remote backup. 2. Disconnect the server from the network while it runs. 3. Reconnect it and refresh the app. Technical verification: 4. Check both the client log and the server-side task log. | The app reports the lost connection clearly instead of hanging or crashing, and it reconnects and shows accurate status once the server is back. Technical verification: Both sides record the interruption and the server-side task ends in a failed state rather than being left permanently marked as running.
18. Reliability & Edge Cases | 18.2 |  | Server reboot | 1. Reboot a connected server. 2. Wait for it to come back and use the app normally. | The app shows the server as offline while it is down, and reconnects afterwards without needing a restart of the app.
18. Reliability & Edge Cases | 18.3 |  | Two backups at once | 1. Start two backup tasks so they run at the same time. Technical verification: 2. Make one a local (client-driven) task and the other a remote (server-side) task so both schedulers run at once. | Both complete successfully, both show separate progress, and neither corrupts the other's data. Technical verification: Both complete, neither blocks the other, and there is no contention over the same mount or dataset.
18. Reliability & Edge Cases | 18.4 |  | Large data set | 1. Back up a folder of at least 20 GB or 50,000 files. 2. Use the app normally while it runs. Technical verification: 3. Watch the app's memory and CPU usage in Task Manager / Activity Monitor / top while it runs. | The backup completes successfully and the app stays responsive throughout. Technical verification: Memory does not grow without bound, the UI thread is never blocked, and progress reporting stays accurate throughout.
18. Reliability & Edge Cases | 18.5 |  | Leave the app running for an extended period | 1. Leave the app open with scheduled tasks for several hours or overnight. 2. Check on it the next working session. Technical verification: 3. Compare the app's memory usage at the start and end of the period. 4. Check for stale mounts and orphaned helper processes afterwards. | The app is still running and responsive, scheduled backups ran on time, and status information is current. Technical verification: No significant memory growth, no leaked mounts, and no orphaned child processes.
18. Reliability & Edge Cases | 18.6 |  | Cancel setup part way through | 1. Start a server setup and go a few steps in. 2. Navigate away or close the wizard before applying. 3. Return to the Dashboard and start again. | The app handles the abandoned setup cleanly, leaves the server untouched, and lets you start over without error.
18. Reliability & Edge Cases | 18.7 |  | Uninstall the app - run this last (Windows) | 1. Delete any remaining backup tasks from within the app. 2. Uninstall 45Drives Storage Wizard through Windows Settings. 3. Open Task Scheduler and confirm no Houston backup tasks remain. Technical verification: 4. Confirm %LOCALAPPDATA%\houston-backups is either cleaned up or intentionally retained per documented behaviour. | The app uninstalls cleanly with no leftover scheduled backup tasks or error dialogs. Technical verification: No orphaned scheduled tasks, scripts, or credential files remain. Anything deliberately retained is documented.

## Instructions
45Drives Storage Wizard - Windows Test Plan (Technical Edition)
Who this is for
This is the technical edition. Every test has the same plain-English steps as the standard edition,
plus a 'Technical verification' block that tells you how to confirm the result on the underlying system.
You will need a terminal on both this machine and the servers, and sudo/administrator rights on the servers.
Angle-bracket placeholders such as <pool> or <user> must be replaced with your real values.
If the plain steps pass but the technical verification does not, that is still a FAIL - record both.
How to Use This Test Plan
1. Work down the Test Plan sheet in order. Later tests often rely on earlier ones having been done.
2. For each test, follow the Steps column and compare what you see to the Expected Result.
3. Enter PASS or FAIL in the Pass/Fail column.
4. If it fails, write what actually happened in Actual Result and why in Notes / Failure Reason.
5. Rate Severity: Critical / High / Medium / Low.
6. Attach a screenshot for anything that fails or looks wrong.
7. If you cannot run a test, write 'BLOCKED - depends on X.Y' in Notes and move on.
What is in scope
The desktop app on Windows, the server setup it performs, the backups and restores it drives,
and the server tools it embeds (Super Simple Setup, Task Scheduler, ZFS, WireShield).
Why rsync and ZFS replication are each tested twice
Sections 11 and 12 run each task type against a plain LAN address. Section 14 runs the same two task types
again using a WireShield tunnel address. That second pass is not a repeat: it proves the address handed back
from WireShield is usable and that SSH, routing and transfer all work over the WireGuard interface.
Cloud backup is run once only, because it goes directly to the provider and never uses the tunnel.
What is deliberately NOT in scope
- WireShield pairing and tunnel management as features in their own right. They are already tested.
Only the handoff between a backup task and WireShield, and backups run over the tunnel, are covered here.
- Exhaustive option-by-option coverage of rsync, cloud, and ZFS replication tasks. These are live and stable.
One working task of each type is enough.
- Cloud provider token expiry and access revocation.
- Saved credentials going stale after 30 days - this cannot be triggered within a test window.
Severity Definitions
Critical - The app crashes, data is lost, or something insecure happens
High - A feature is completely broken with no way around it
Medium - A feature is partly broken but there is a workaround
Low - Cosmetic or a minor annoyance
Test Environment Prerequisites
- Two 45Drives servers on the same network. At least one with 6 or more drives so Split Pools can be tested.
- A third unconfigured server, or the ability to reset one, for the bulk setup and custom setup runs.
- One cloud account you sign in to (Dropbox or Google Drive) and one that uses keys (S3, Wasabi, or Backblaze B2).
- Internet access from both servers so the two can pair over WireShield.
- Test files including a large file (1 GB+) and files with spaces and accented characters in their names.
- A build of the app one version behind the latest release, so the update tests have something to find.
Note on the WireShield tunnel tests
Both servers are on the same network for this test pass, so the tunnel tests exercise the local path only.
Confirm traffic really went through the tunnel by checking the connection's sent/received counters
before and after each backup that uses the tunnel address.
Reference
docs/45Drives_Storage_Wizard_User_Guide.md